# Observability SDK Migration — Project Plan

Observability SDK Migration — Project Plan

Project Plan

1. Executive Summary 2. Project Background 3. Project Scope 4. Current Status 5. Objectives 6. Migration Strategy 7. Migration Lifecycle 8. Microservice Assessment 9. Endpoint Inventory Template 10. Critical Endpoint Classification 11. Observability Design 12. Dashboard Requirements 13. Alert Strategy 14. Migration Playbook 15. Sprint Plan 16. Project Tracker 17. Risks 18. Dependencies 19. Governance 20. Definition of Done 21. Success Metrics 22. Lessons Learned 23. Appendices

# Observability SDK Migration

Project Plan — Tugane Platform, Development Bank of Rwanda · July 2026

## 1Executive Summary

The Tugane platform operates 11 NestJS microservices that collectively handle guarantees, loans, procurement, payments, and monitoring for BRD Rwanda. Each service was built with its own observability stack—Winston loggers, Morgan middleware, custom LoggerService classes, Kafka-based log shipping, and hand-rolled HTTP exception filters. The result: no trace correlation across services, no distributed tracing, inconsistent log formats, no unified metrics, and no way to diagnose cross-service failures without manually reading logs on individual machines.

### Current State

- 11 microservices, each with duplicated logging infrastructure (Winston + Morgan + LoggerService + Kafka logging client)

- No distributed tracing—requests crossing service boundaries lose all context

- No standardized metrics—no RED dashboards, no SLO tracking, no alerting on error rates

- Debugging production issues requires SSH into individual machines and grepping log files

- Mean Time to Detect (MTTD) and Mean Time to Resolve (MTTR) are unmeasured and high

### Future State

- Every service instrumented with @brdrwanda/observability—structured JSON logs with trace_id, request_id, and span_id on every line

- Distributed traces flow across all service boundaries via W3C traceparent propagation

- Prometheus metrics (RED: Rate, Errors, Duration) exported automatically per service

- Grafana dashboards with bidirectional signal correlation: metrics → traces → logs → metrics

- Automated alerting on error rate spikes, high latency, service down, and log anomalies

### Timeline & Progress

| Metric | Value |
| --- | --- |
| Services with SDK installed | 5 / 11 (45%) |
| Services with legacy fully removed | 0 / 11 (0%) |
| Estimated total duration | 8–10 sprints (2-week sprints) |
| Infrastructure readiness | Complete OTel Collector, Tempo, Loki, Prometheus, Grafana deployed |

### Expected Business Outcomes

- MTTR reduction: From hours of log-grepping to minutes via trace-correlated dashboards

- Proactive detection: Automated alerts catch degradation before users report it

- Developer velocity: New services get full observability with 5 lines of config, not 200+ lines of boilerplate

- Operational consistency: One dashboard layout, one log format, one alerting strategy across all services

### Success Metrics

| KPI | Target |
| --- | --- |
| SDK adoption | 11/11 services (100%) |
| Legacy code removal | 0 Winston/Morgan/LoggerService references |
| Trace coverage | 100% of HTTP requests carry trace_id end-to-end |
| Dashboard coverage | Every service has a RED + Runtime + Logs dashboard |
| Alert coverage | Error rate, latency, and availability alerts on every service |
| MTTR | < 30 minutes for P1 incidents (from first alert to root cause identified) |

## 2Project Background

### Existing Observability Challenges

Every Tugane service was built independently with a copy-pasted logging pattern:

| Component | What it does | Problem |
| --- | --- | --- |
| LoggerService | Extends NestJS Logger, wraps Winston with context | Duplicated in every service (50+ files reference it). No trace correlation. |
| Winston + DailyRotateFile | Writes JSON logs to rotating files | Logs stored on local disk. Lost on container restart. No centralized search. |
| Morgan middleware | HTTP access logging | Separate format from Winston. Duplicates request/response logging. |
| Kafka log producer | Ships logs to logging.info/logging.warn topics | Extra latency on every request. Kafka dependency for logging creates cascading failures. |
| HttpExceptionFilter | Catches exceptions, logs them | Custom per-service. Inconsistent error classification. |
| createLoggingContextWithId | Manual correlation IDs | Developer must remember to call it. IDs don't propagate across services. |

### Why the SDK Was Built

The @brdrwanda/observability SDK was purpose-built to replace this entire stack with a single, zero-config package that provides:

- Structured logging (Pino) with automatic trace context injection—every log line gets trace_id, span_id, request_id without developer effort

- Distributed tracing via OpenTelemetry with W3C traceparent propagation

- Prometheus metrics (HTTP RED metrics, Node.js runtime, custom business metrics)

- Health checks (/health endpoint) for Kubernetes readiness/liveness probes

- Auto-instrumentation of HTTP, Kafka, Redis, Sequelize, and scheduled jobs

- Error classification (401→authentication_failed, 400→validation_failed, 500→server_error)

### Why Migration Is Necessary

Simply installing the SDK alongside existing code creates conflicts—two logging systems writing to stdout, two exception filters competing, and the legacy LoggerService continuing to produce unstructured logs that bypass trace context. The legacy code must be systematically removed per-service to realize the SDK's full value.

## 3Project Scope

### In Scope

| Area | Description |
| --- | --- |
| SDK Adoption | Install and configure @brdrwanda/observability in all 11 services |
| Logging Migration | Replace Winston, Morgan, LoggerService, createLoggingContextWithId with SDK's Pino-based logger |
| Metrics | Enable Prometheus metrics export on every service; define business-specific metrics per service |
| Tracing | Enable distributed tracing with OTLP export; instrument HTTP, Kafka, Redis, Sequelize, scheduled jobs |
| Dashboards | Provision Grafana dashboards per service (RED, Runtime, Logs, Dependencies) |
| Alerting | Configure Prometheus and Grafana alerts for each service |
| Legacy Removal | Delete all old logging infrastructure: Winston config, Morgan middleware, Kafka log producers, custom LoggerService |
| Scheduled Job Tracing | Instrument @Cron, @Interval, @Timeout handlers with automatic trace context |

### Out of Scope

| Area | Rationale |
| --- | --- |
| Business logic changes | No functional behavior changes. Observability is additive. |
| API contracts | No endpoint signatures, request/response schemas, or HTTP status codes change |
| Database schema | No migrations. SDK instruments queries at the driver level. |
| UI / Frontend | No frontend changes. Observability is backend-only. |
| Feature development | Migration sprints are dedicated to observability. New features are separate. |
| Infrastructure provisioning | Grafana stack (Tempo, Loki, Prometheus, OTel Collector) is already deployed |

## 4Current Status

Data below is derived from codebase analysis on 28 July 2026. SDK installed = @brdrwanda/observability found in package.json. Legacy references = files containing Winston, Morgan, or LoggerService imports.

| Microservice | Port | SDK Installed | Legacy Removal | Endpoint Inventory | Metrics Defined | Progress |
| --- | --- | --- | --- | --- | --- | --- |
| API Gateway | 7070 | Yes | In Progress | Not Started | Not Started | 20% |
| Access Management | 9000 | Yes | In Progress | Not Started | Not Started | 20% |
| Authentication | 8000 | Yes | In Progress | Not Started | Not Started | 20% |
| Application Service | 9004 | Yes | In Progress | Not Started | Not Started | 15% |
| Job Scheduler | 3001 | Yes | In Progress | Not Started | Not Started | 20% |
| Product Service | 8100 | No | Not Started | Not Started | Not Started | 0% |
| Payment Service | 8800 | No | Not Started | Not Started | Not Started | 0% |
| Configuration Service | 8008 | No | Not Started | Not Started | Not Started | 0% |
| MEL Service | 8600 | No | Not Started | Not Started | Not Started | 0% |
| Workflow Service | 8444 | No | Not Started | Not Started | Not Started | 0% |
| Profile Service | 8092 | No | Not Started | Not Started | Not Started | 0% |

### Legacy Code Inventory

Even services with SDK installed still contain significant legacy code. The SDK is running alongside the old stack. Full value requires legacy removal.

| Service | Winston refs | Morgan refs | LoggerService refs | HttpExceptionFilter | Effort |
| --- | --- | --- | --- | --- | --- |
| API Gateway | 3 | 2 | 25 | 2 | High |
| Authentication | 2 | 2 | 10 | 2 | Medium |
| Application Service | 2 | 2 | 6 | 1 | Medium |
| Job Scheduler | 2 | 2 | 6 | 2 | Medium |
| Access Management | 1 | 2 | 5 | 1 | Low |
| Product Service | 1 | 2 | 11 | — | Medium |
| Payment Service | 1 | 2 | 8 | — | Medium |
| Configuration | 1 | 2 | 4 | — | Low |
| MEL Service | 1 | 2 | 4 | — | Low |
| Workflow Service | 1 | 2 | 4 | — | Low |
| Profile Service | 2 | 2 | 4 | — | Low |

## 5Objectives

### Technical Objectives

- Standardize observability infrastructure across all 11 microservices using a single SDK

- Achieve end-to-end distributed tracing from API Gateway through every downstream service

- Enable Prometheus metrics collection with consistent naming and labeling

- Instrument all communication channels: HTTP, Kafka, Redis, Sequelize, scheduled jobs

- Correlate all three signals (logs, traces, metrics) bidirectionally in Grafana

### Business Objectives

- Reduce MTTR: Enable root-cause analysis in minutes instead of hours by following a single trace_id across all services

- Improve troubleshooting: Any engineer can diagnose a production issue using Grafana without SSH access to servers

- Standard dashboards: Every service gets the same RED dashboard layout, reducing cognitive load when context-switching between services

- Faster onboarding: New developers and new services get full observability with 5 lines of config

### Operational Objectives

- Eliminate duplicated code: Remove ~90 files of copy-pasted logging infrastructure across 11 services

- Centralize instrumentation: SDK updates propagate to all services via npm update instead of copy-pasting changes

- Remove Kafka logging dependency: Logs flow to Loki via Promtail/stdout, eliminating the fragile Kafka-based log shipping

- Enable SLO tracking: Standardized metrics enable defining and tracking Service Level Objectives

## 6Migration Strategy

### Three-Level Approach

We migrate one service at a time, not everything simultaneously. Each service progresses through three levels. A service at Level 1 is already delivering value; Level 3 is full completion.

| Level | Name | Outcome | Effort |
| --- | --- | --- | --- |
| L1 | Platform Readiness | SDK installed, exporters configured, core infrastructure connected. Service emits traces and metrics alongside legacy code. | 0.5–1 day |
| L2 | Observability Design | Endpoints inventoried, critical flows identified, metrics/logs/traces/dashboards/alerts designed per endpoint. | 1–2 days |
| L3 | Legacy Migration & Validation | Legacy code removed, SDK is sole observability provider, dashboards published, alerts configured, production validated. | 2–5 days (varies by service complexity) |

### Per-Service Migration Flow

Select
Service

→

Endpoint
Inventory

→

Classify
Endpoints

→

Design
Observability

→

SDK
Migration

→

Validate
& Test

→

Deploy to
Production

### Recommended Migration Order

| Priority | Service | Rationale |
| --- | --- | --- |
| 1 | Access Management | Smallest codebase (3 controllers). SDK already installed. Lowest legacy debt (5 LoggerService refs). Authorization dependency for all services—high observability value. |
| 2 | Job Scheduler | SDK installed. Cron tracing already built. No inbound API traffic—isolated risk. Tests scheduled job observability end-to-end. |
| 3 | Authentication | SDK installed. Critical path for all user requests. 10 LoggerService refs to replace. |
| 4 | API Gateway | SDK installed but highest legacy debt (25 LoggerService refs, 59 controllers). Largest blast radius—do after gaining confidence from smaller services. |
| 5 | Configuration Service | Small service (2 controllers, 4 LoggerService refs). Quick win to start non-SDK services. |
| 6 | Workflow Service | Small footprint (2 controllers). Approval workflows benefit from tracing. |
| 7 | Profile Service | Small footprint (6 controllers, 4 LoggerService refs). |
| 8 | Product Service | Medium size. 11 LoggerService refs. |
| 9 | Payment Service | Financial transactions—higher care needed. 8 LoggerService refs. |
| 10 | MEL Service | Reports/KPIs. Can run in parallel with others. |
| 11 | Application Service | Largest service (24 controllers, 45 services, 328 Sequelize refs). Highest complexity—last to minimize risk. |

## 7Migration Lifecycle

1

#### Service Assessment

Purpose

Understand the service's architecture, dependencies, and current observability to estimate migration effort.

Owner

Developer + SRE

Duration

0.5 days

Dependencies

Access to source code and running environment

#### Activities

- Catalog controllers, services, modules, and their responsibilities

- Identify external dependencies (databases, Kafka topics, Redis, external APIs)

- Count legacy observability references (Winston, Morgan, LoggerService, HttpExceptionFilter)

- Identify critical business flows that transit the service

- Assess migration complexity (Low / Medium / High)

Inputs

Source code, architecture docs, team knowledge

Outputs

Completed Microservice Assessment (Section 8)

Entry Criteria

Service selected for migration

Exit Criteria

Assessment reviewed and approved by tech lead

Deliverables

Microservice Assessment document

2

#### Endpoint Inventory

Purpose

Understand every endpoint exposed by the service, who consumes it, and what observability exists today.

Owner

Developer + SRE

Duration

1–2 days

Dependencies

Completed assessment; Swagger docs if available

#### Activities

- List all REST endpoints (method, path, controller, handler)

- List all Kafka consumers and producers with topic names

- List all scheduled jobs (@Cron, @Interval, @Timeout)

- Identify consumers of each endpoint (Gateway, other services, external)

- Document business capability each endpoint serves

- Catalog existing logging, metrics, and tracing per endpoint

Inputs

Source code, Swagger/OpenAPI, API Gateway routing config

Outputs

Endpoint Inventory (Section 9)

Entry Criteria

Assessment approved

Exit Criteria

Inventory reviewed; every endpoint accounted for

Deliverables

Endpoint Inventory spreadsheet/document

3

#### Critical Endpoint Classification

Purpose

Prioritize observability investment by scoring endpoints on business impact.

Owner

Developer + PM + Business Analyst

Duration

0.5 days

Dependencies

Completed endpoint inventory

#### Activities

- Score each endpoint using the classification model (Section 10)

- Classify into Critical / High / Medium / Low tiers

- Validate classification with business stakeholders

- Critical endpoints get full observability design; Low endpoints get SDK defaults only

Inputs

Endpoint inventory, business context

Outputs

Classified endpoint list with priority tiers

Entry Criteria

Endpoint inventory complete

Exit Criteria

Classification reviewed by PM and tech lead

Deliverables

Classified endpoint matrix

4

#### Observability Design

Purpose

Define exactly what logs, metrics, traces, dashboards, and alerts each endpoint needs before writing code.

Owner

SRE + Developer

Duration

1–2 days

Dependencies

Classified endpoints; SDK capabilities documented

#### Activities

- For Critical/High endpoints: design logs (events, severity, fields), metrics (name, type, labels), traces (spans, expected duration)

- For Medium/Low endpoints: confirm SDK defaults are sufficient

- Design service-level dashboard layout (widgets, data sources)

- Define alert thresholds, severity, and escalation

- Document sensitive fields that need redaction

Inputs

Classified endpoints, SDK capabilities, existing dashboards as templates

Outputs

Observability Design document (Section 11)

Entry Criteria

Endpoint classification approved

Exit Criteria

Design reviewed by SRE and tech lead

Deliverables

Observability Design per service

5

#### SDK Migration

Purpose

Replace legacy observability with the SDK and implement the observability design.

Owner

Developer

Duration

2–5 days (varies by service size)

Dependencies

Observability design approved; SDK version locked

#### Activities

- Install SDK and configure ObservabilityModule.forRoot()

- Replace NestJS Logger with NestPinoLogger in main.ts

- Replace all LoggerService injections with ObservabilityLogger

- Remove Winston, Morgan, Kafka log producer, createLoggingContextWithId

- Remove custom HttpExceptionFilter (SDK provides one)

- Add @Span() decorators on critical business methods per design

- Add custom metrics per design

- Implement trace propagation on inter-service HTTP calls

- Delete unused logging files, middleware, and dependencies

Inputs

Observability design, migration checklist (Section 14)

Outputs

Migrated service code, PR for review

Entry Criteria

Design approved; local sandbox running

Exit Criteria

All legacy references removed; all tests pass; PR approved

Deliverables

Pull request with migration changes

6

#### Validation & Testing

Purpose

Verify that the migration works end-to-end and all observability signals are correct.

Owner

Developer + SRE + QA

Duration

1–2 days

Dependencies

Migration PR merged to staging branch; sandbox infrastructure running

#### Activities

- Run service locally against sandbox (OTel Collector, Tempo, Loki, Prometheus, Grafana)

- Verify structured logs appear in Grafana Loki with trace_id

- Verify traces appear in Grafana Tempo with correct span hierarchy

- Verify metrics appear in Prometheus with correct labels

- Verify dashboards populate with real data

- Verify alerts fire on simulated conditions

- Test distributed trace propagation with upstream/downstream services

- Verify no legacy log output remains

- Verify no console.log statements remain

- Load test to ensure no performance regression

Inputs

Migrated code, sandbox environment

Outputs

Validation report with screenshots

Entry Criteria

Migration PR approved and merged to staging

Exit Criteria

All validation checks pass

Deliverables

Validation checklist (signed off), Grafana screenshots

7

#### Production Deployment & Hypercare

Purpose

Deploy the migrated service to production and monitor for regressions.

Owner

SRE + Developer

Duration

1 day deploy + 3–5 days hypercare

Dependencies

Validation passed; rollback plan documented; team availability confirmed

#### Activities

- Deploy during low-traffic window

- Monitor dashboards for anomalies in first hour

- Verify logs, traces, and metrics flowing in production Grafana

- 3–5 day hypercare period: daily dashboard review, alert tuning

- Adjust alert thresholds based on production traffic patterns

- Document any issues and resolutions

Inputs

Validated code, rollback plan, deployment runbook

Outputs

Production service with full observability

Entry Criteria

All validation checks pass; rollback plan approved

Exit Criteria

5 days stable in production; no rollback needed; alerts tuned

Deliverables

Production validation report, updated Definition of Done (Section 20)

## 8Microservice Assessment Template

Every service gets a completed assessment before migration begins. Below are assessments based on codebase analysis.

### API Gateway

| Attribute | Value |
| --- | --- |
| Purpose | Public edge router. Single entry point for all client requests. Routes to downstream services via HTTP. |
| Port | 7070 |
| Controllers / Services / Modules | 59 / 58 / 51 |
| Dependencies | Redis (caching), Kafka (logging client) |
| External Systems | All downstream microservices via HTTP |
| Database | None (stateless proxy) |
| Kafka Topics | logging.info, logging.warn (producer) |
| Critical Flows | Authentication routing, loan applications, guarantee applications, payment routing |
| Current Observability | SDK installed. Legacy remains: 3 Winston, 2 Morgan, 25 LoggerService, 2 HttpExceptionFilter refs |
| Migration Complexity | High — largest codebase, highest number of legacy references |
| Estimated Effort | 5 days (migration) + 2 days (validation) |

### Access Management Service

| Attribute | Value |
| --- | --- |
| Purpose | Role-based access control. Every authenticated request checks permissions here. |
| Port | 9000 |
| Controllers / Services / Modules | 3 / 4 / 4 |
| Dependencies | Redis (caching), Kafka, Sequelize (MSSQL) |
| Database | MSSQL (Sequelize) — roles, permissions, role-access mappings |
| Kafka Topics | logging.info, logging.warn |
| Critical Flows | Role-access authorization (called on every authenticated request) |
| Current Observability | SDK installed. Legacy: 1 Winston, 2 Morgan, 5 LoggerService, 1 HttpExceptionFilter |
| Migration Complexity | Low |
| Estimated Effort | 1 day (migration) + 1 day (validation) |

### Authentication Service

| Attribute | Value |
| --- | --- |
| Purpose | User authentication, JWT issuance, user management. |
| Port | 8000 (called as 9001 from Gateway) |
| Controllers / Services / Modules | 6 / 17 / 6 |
| Dependencies | Redis, Kafka, Sequelize (MSSQL) |
| Database | MSSQL (63 Sequelize references) — users, sessions, OTP |
| Critical Flows | Login, JWT issuance, token refresh, OTP verification, password reset |
| Current Observability | SDK installed. Legacy: 2 Winston, 2 Morgan, 10 LoggerService, 2 HttpExceptionFilter |
| Migration Complexity | Medium |
| Estimated Effort | 2 days (migration) + 1 day (validation) |

### Application Service

| Attribute | Value |
| --- | --- |
| Purpose | Core domain service for guarantee and loan applications. |
| Port | 9004 |
| Controllers / Services / Modules | 24 / 45 / 28 |
| Dependencies | Redis, Kafka, Sequelize (MSSQL) |
| Database | MSSQL (328 Sequelize references) — applications, forms, guarantees, loans |
| Critical Flows | Application submission, guarantee issuance, loan processing, form management |
| Current Observability | SDK installed. Legacy: 2 Winston, 2 Morgan, 6 LoggerService, 1 HttpExceptionFilter |
| Migration Complexity | High — largest domain logic, heaviest DB usage |
| Estimated Effort | 5 days (migration) + 2 days (validation) |

### Job Scheduler (Uno)

| Attribute | Value |
| --- | --- |
| Purpose | Cron-only service. No inbound API traffic. Pulls work periodically and integrates with external government systems (MINECOFIN, RIM). |
| Port | 3001 |
| Controllers / Services / Modules | 4 / 7 / 6 |
| Dependencies | Redis, Kafka, Sequelize (MSSQL) |
| External Systems | MINECOFIN, RIM (government APIs) |
| Database | MSSQL (12 Sequelize references) |
| Critical Flows | Application status sync, external integration cron jobs, payment scheduling |
| Current Observability | SDK installed. Cron tracing built (auto @Cron/@Interval/@Timeout instrumentation). Legacy: 2 Winston, 2 Morgan, 6 LoggerService |
| Migration Complexity | Medium |
| Estimated Effort | 2 days (migration) + 1 day (validation) |

### Services Without SDK (Summary)

| Service | Port | Controllers | Services | Sequelize Refs | Legacy Logger Refs | Complexity | Est. Effort |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Product | 8100 | 6 | 8 | 34 | 11 | Medium | 2–3 days |
| Payment | 8800 | 4 | 8 | 26 | 8 | Medium | 2–3 days |
| Configuration | 8008 | 2 | 8 | 19 | 4 | Low | 1–2 days |
| MEL | 8600 | 8 | 10 | 75 | 4 | Medium | 2–3 days |
| Workflow | 8444 | 2 | 10 | 35 | 4 | Low | 1–2 days |
| Profile | 8092 | 6 | 7 | 25 | 4 | Low | 1–2 days |

## 9Endpoint Inventory Template

Complete one row per endpoint for each service. Example for Access Management:

| Endpoint | Method | Business Capability | Consumer | Criticality | Current Logs | Current Metrics | Current Traces |
| --- | --- | --- | --- | --- | --- | --- | --- |
| /api/role-access | GET | Authorization check | All services (every authenticated request) | Critical | Winston info | None | None |
| /api/role-access | POST | Create role-access mapping | Admin portal via Gateway | High | Winston info | None | None |
| /api/role-access/:id | PUT | Update role-access mapping | Admin portal via Gateway | High | Winston info | None | None |
| /api/role-access/:id | DELETE | Revoke role-access mapping | Admin portal via Gateway | High | Winston info | None | None |
| /health | GET | Health check | Kubernetes, monitoring | Low | None | SDK auto | SDK auto |
| /metrics | GET | Prometheus scrape | Prometheus | Low | None | SDK auto | Excluded |

## 10Critical Endpoint Classification

### Scoring Model

| Criteria | Weight | Description |
| --- | --- | --- |
| Customer Impact | High | Does a failure directly affect end users (loan applicants, bank staff)? |
| Financial Impact | High | Does the endpoint handle money movement, guarantees, or financial calculations? |
| Security | High | Does it handle authentication, authorization, or sensitive data? |
| Usage Frequency | Medium | How many requests per day? High-frequency endpoints need tighter alerting. |
| Upstream Dependencies | Medium | How many other services depend on this endpoint? Single-point-of-failure risk. |

### Classification Tiers

| Tier | Criteria | Observability Treatment |
| --- | --- | --- |
| Critical | 2+ High-weight criteria score high | Full custom design: dedicated metrics, custom spans, specific alerts, dashboard widget, runbook |
| High | 1 High-weight + 1 Medium-weight score high | Custom metrics and alerts. SDK-default logging and tracing. |
| Medium | 1–2 Medium-weight criteria score high | SDK defaults with specific log events on key actions. |
| Low | No criteria score high | SDK defaults only. No custom metrics or alerts. |

### Example Classification: Authentication Service

| Endpoint | Customer | Financial | Security | Frequency | Dependencies | Tier |
| --- | --- | --- | --- | --- | --- | --- |
| POST /auth/login | High | Low | High | High | High | Critical |
| POST /auth/refresh | High | Low | High | High | High | Critical |
| POST /auth/otp/verify | High | Low | High | Medium | Medium | Critical |
| POST /auth/register | Medium | Low | High | Low | Low | High |
| POST /auth/password/reset | Medium | Low | High | Low | Low | High |
| GET /auth/users | Low | Low | Medium | Low | Low | Medium |

## 11Observability Design

### Logs

For every Critical/High endpoint, define:

| Attribute | Description |
| --- | --- |
| Events | What log events should this endpoint emit? (e.g., login_attempt, login_success, login_failure) |
| Severity | What log level for each event? (info for success, warn for client errors, error for server errors) |
| Fields | What structured fields beyond SDK defaults? (e.g., user_id, client_ip, auth_provider) |
| Correlation IDs | SDK provides trace_id, request_id, span_id automatically. Add business IDs? (e.g., application_id, guarantee_id) |
| Sensitive Fields | What fields need redaction? SDK auto-redacts passwords/tokens. Add service-specific? (e.g., national_id, phone_number) |

#### Example: Authentication Service — POST /auth/login

| Event | Level | Fields | When |
| --- | --- | --- | --- |
| login_attempt | info | username, client_ip, auth_provider | Request received |
| login_success | info | user_id, username, session_duration | JWT issued |
| login_failure | warn | username, failure_reason, attempt_count | Authentication rejected |
| account_locked | error | username, lock_duration, attempt_count | Max attempts exceeded |

### Metrics

SDK provides HTTP RED metrics automatically. Define business-specific metrics per service:

#### Example Metrics Catalogue

| Metric Name | Type | Labels | Description | Alert | Dashboard |
| --- | --- | --- | --- | --- | --- |
| login_attempts_total | Counter | status, provider | Total login attempts | Failure rate >5% for 5min | Authentication Overview |
| active_sessions_total | Gauge | user_type | Currently active JWT sessions | Spike >200% of baseline | Authentication Overview |
| guarantee_applications_total | Counter | status, type | Guarantee applications processed | — | Application Overview |
| payment_processing_duration_seconds | Histogram | payment_type, status | Time to process a payment | p95 >10s for 5min | Payment Overview |
| external_api_duration_seconds | Histogram | target, status | External API call latency (MINECOFIN, RIM) | p95 >30s for 5min | Job Scheduler Overview |
| cron_job_duration_seconds | Histogram | job_name, status | Scheduled job execution time | Error rate >10% | Job Scheduler Overview |

### Traces

For each Critical endpoint, define the expected span tree:

#### Example: Loan Application Submission

| Span | Kind | Service | Expected Duration |
| --- | --- | --- | --- |
| POST /api/applications | Server | API Gateway | <50ms (proxy) |
| ↳ POST /applications | Server | Application Service | <2s |
| ↳ Sequelize: INSERT applications | Client | Application Service | <200ms |
| ↳ Sequelize: INSERT guarantee_details | Client | Application Service | <200ms |
| ↳ Kafka: produce application.created | Producer | Application Service | <100ms |
| ↳ GET /api/role-access | Client | Access Management | <50ms |

## 12Dashboard Requirements

### Standard Dashboard Set (Per Service)

| Dashboard | Widgets | Data Source | Refresh |
| --- | --- | --- | --- |
| Service Overview (RED) | Request rate, error rate, p50/p95/p99 latency, status code distribution, top 10 slowest routes, error breakdown by type | Prometheus | 10s |
| Node.js Runtime | Heap memory (used/total), CPU usage, event loop lag, GC duration, active handles/requests | Prometheus | 15s |
| Dependencies | Database query latency (p50/p95), slow query count, Redis hit rate, Kafka produce/consume latency, external API latency | Prometheus | 15s |
| Logs & Traces | Log volume by level (stacked area), recent errors (table), recent traces (table), log search panel | Loki + Tempo | 10s |
| Business Metrics | Service-specific counters and gauges (per observability design) | Prometheus | 30s |
| Availability | Uptime percentage, health check status, pod restarts (if K8s), last deploy timestamp | Prometheus | 30s |

### Cross-Service Dashboards

| Dashboard | Purpose | Widgets |
| --- | --- | --- |
| Platform Overview | Single pane of glass for all services | Service map, per-service error rate heatmap, overall p95, active alerts |
| Distributed Traces | Cross-service request flow | Tempo search panel, service graph, trace duration histogram |

## 13Alert Strategy

### Platform Alerts (All Services)

| Alert | Condition | Severity | Escalation | Owner |
| --- | --- | --- | --- | --- |
| ServiceDown | up == 0 for 1 min | Critical | PagerDuty → Oncall → Team Lead (15 min) | SRE |
| HighErrorRate | 5xx > 5% of requests for 5 min | Critical | Teams → Oncall | SRE |
| HighLatencyP95 | p95 > 2s for 5 min | Warning | Teams channel | Developer |
| HighLatencyP99 | p99 > 5s for 5 min | Critical | Teams → Oncall | SRE |
| HighMemory | Heap > 85% for 10 min | Warning | Teams channel | Developer |
| HighEventLoopLag | Lag > 500ms for 5 min | Warning | Teams channel | Developer |

### Business Alerts (Service-Specific)

| Alert | Service | Condition | Severity | Owner |
| --- | --- | --- | --- | --- |
| AuthFailureSpike | Authentication | Login failures > 1/sec for 5 min | Warning | Security |
| PaymentProcessingDelay | Payment | Payment processing p95 > 30s for 5 min | Critical | Payment team |
| CronJobFailure | Job Scheduler | Cron job error rate > 10% for 15 min | Warning | SRE |
| ExternalAPIDown | Job Scheduler | MINECOFIN/RIM API error rate > 50% for 10 min | Critical | SRE |

### Log-Based Alerts (Grafana/Loki)

| Alert | Condition | Severity |
| --- | --- | --- |
| ErrorLogSpike | Error log rate > 0.5/sec for 5 min | Warning |
| ServiceStoppedLogging | No logs for 10 min | Critical |
| UnhandledRejection | Unhandled promise rejection detected | Critical |

## 14Migration Playbook

This is the step-by-step checklist developers follow for each service. Detailed code examples are in Migration Guide and Migration Checklist.

### 14.1 Preparation

- Completed Microservice Assessment (Section 8)

- Completed Endpoint Inventory (Section 9)

- Completed Endpoint Classification (Section 10)

- Completed Observability Design (Section 11)

- SDK version pinned in package.json

- Local sandbox running (OTel Collector, Tempo, Loki, Prometheus, Grafana)

- Feature branch created from main

### 14.2 Development

- Install SDK: npm install @brdrwanda/observability

- Configure main.ts: setupProcessErrorHandlers(), NestPinoLogger

- Configure app.module.ts: ObservabilityModule.forRoot() with service-specific config

- Add instrumentations: HTTP, Kafka, Redis, Sequelize as needed

- Replace every LoggerService injection with ObservabilityLogger

- Remove createLoggingContextWithId() calls (SDK injects context automatically)

- Remove custom HttpExceptionFilter (SDK provides one via APP_FILTER)

- Remove Morgan middleware from app.module.ts

- Remove Winston configuration and transports

- Remove Kafka logging producer (logging.info / logging.warn topics)

- Add @Span() decorators on critical methods per observability design

- Add custom business metrics per observability design

- Add trace propagation headers on inter-service HTTP calls

- Replace console.log with this.logger.info()

- Delete unused files: logger.service.ts, morgan.middleware.ts, winston.config.ts

- Uninstall packages: npm uninstall winston nest-winston winston-daily-rotate-file morgan

### 14.3 Testing

- All existing tests pass

- Service starts without errors

- Structured JSON logs appear on stdout with trace_id

- No Winston/Morgan output in logs

- /health returns 200

- /metrics returns Prometheus format

- Traces appear in Grafana Tempo

- Logs appear in Grafana Loki

- Metrics appear in Prometheus

- Cross-service trace propagation works (same trace_id in upstream and downstream)

### 14.4 Deployment

- PR reviewed and approved

- Deploy to staging environment

- Staging validation passes (repeat Testing checklist)

- Rollback plan documented and tested

- Deploy to production during low-traffic window

### 14.5 Rollback Plan

- Previous deployment artifact retained

- Rollback trigger: error rate >10% or service-down alert within 30 min of deploy

- Rollback action: redeploy previous version via CI/CD

- Rollback verification: error rate returns to baseline, service healthy

- Post-rollback: root cause analysis, fix, re-attempt migration

### 14.6 Validation & Closeout

- Production dashboards populate with real data

- Alerts configured and tested

- 5-day hypercare period completed without rollback

- Definition of Done checklist completed (Section 20)

- Lessons learned documented (Section 22)

- Service marked complete in Project Tracker (Section 16)

## 15Sprint Plan

| Sprint | Duration | Services | Deliverables | Exit Criteria |
| --- | --- | --- | --- | --- |
| Sprint 1 | 2 weeks | Access Management, Job Scheduler | Both services fully migrated. Legacy removed. Dashboards published. Alerts configured. | DoD checklist complete for both. Production hypercare passed. |
| Sprint 2 | 2 weeks | Authentication | Auth service migrated. Login/session metrics designed. Security alerts configured. | DoD checklist complete. Distributed traces from Gateway → Auth working. |
| Sprint 3 | 2 weeks | API Gateway | Gateway migrated (highest effort service). All 25 LoggerService refs replaced. | DoD checklist complete. End-to-end traces from Gateway to all downstream services. |
| Sprint 4 | 2 weeks | Configuration, Workflow, Profile | Three smaller services migrated in parallel. | DoD checklist complete for all three. |
| Sprint 5 | 2 weeks | Product, Payment | Product and Payment migrated. Payment-specific metrics and alerts configured. | DoD checklist complete. Payment alerting validated. |
| Sprint 6 | 2 weeks | MEL Service | MEL migrated. KPI/report-specific metrics. | DoD checklist complete. |
| Sprint 7–8 | 4 weeks | Application Service | Largest service migrated. All 328 Sequelize refs instrumented. Guarantee/loan flow traces. | DoD checklist complete. Full platform service map in Grafana. |
| Sprint 9 | 2 weeks | Platform-wide | Cross-service dashboards. Platform overview dashboard. SLO definitions. Documentation. | All 11 services green. All dashboards published. Alert runbooks written. |

## 16Project Tracker

| Service | Assessment | Inventory | Classification | Design | SDK Migration | Legacy Cleanup | Validation | Production |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Access Mgmt | Done | Todo | Todo | Todo | Partial | Todo | Todo | Todo |
| Job Scheduler | Done | Todo | Todo | Todo | Partial | Todo | Todo | Todo |
| Authentication | Done | Todo | Todo | Todo | Partial | Todo | Todo | Todo |
| API Gateway | Done | Todo | Todo | Todo | Partial | Todo | Todo | Todo |
| Application | Done | Todo | Todo | Todo | Partial | Todo | Todo | Todo |
| Configuration | Done | Todo | Todo | Todo | Todo | Todo | Todo | Todo |
| Workflow | Done | Todo | Todo | Todo | Todo | Todo | Todo | Todo |
| Profile | Done | Todo | Todo | Todo | Todo | Todo | Todo | Todo |
| Product | Done | Todo | Todo | Todo | Todo | Todo | Todo | Todo |
| Payment | Done | Todo | Todo | Todo | Todo | Todo | Todo | Todo |
| MEL | Done | Todo | Todo | Todo | Todo | Todo | Todo | Todo |

## 17Risks

### Technical Risks

| Risk | Probability | Impact | Mitigation | Owner |
| --- | --- | --- | --- | --- |
| SDK update introduces breaking change | Low | High | Pin SDK version per service. Test upgrades in sandbox before production. | SRE |
| OTel Collector becomes bottleneck | Low | Medium | Monitor Collector metrics. Scale horizontally if needed. SDK has batch export with backpressure. | SRE |
| Performance regression from tracing overhead | Low | Medium | SDK uses sampling (configurable ratio). Load test each migrated service. Disable tracing per-service if needed. | Developer |
| Incomplete legacy removal causes dual logging | Medium | Low | Legacy code inventory (Section 4) tracks exact file/line counts. DoD requires zero legacy refs. | Developer |
| OpenTelemetry v1/v2 dependency conflicts | Medium | Medium | SDK bundles OTel v2. Services must not independently install OTel v1 packages. Migration guide documents this. | Developer |

### Operational Risks

| Risk | Probability | Impact | Mitigation | Owner |
| --- | --- | --- | --- | --- |
| Grafana stack storage grows unbounded | Medium | Medium | Configure retention: Loki 30d, Tempo 14d, Prometheus 30d. Monitor disk usage. | SRE |
| Alert fatigue from noisy thresholds | High | Medium | Start with conservative thresholds. Tune during hypercare. Weekly alert review first month. | SRE |
| Team lacks Grafana/OTel expertise | Medium | Medium | SDK abstracts OTel complexity. Provide Grafana training session. Document common queries. | SRE |

### Project Risks

| Risk | Probability | Impact | Mitigation | Owner |
| --- | --- | --- | --- | --- |
| Developer bandwidth pulled to feature work | High | High | Dedicated sprint capacity for migration. PM blocks conflicting feature work. | PM |
| Application Service migration takes longer than estimated | Medium | Medium | Scheduled last. Learnings from 10 prior services reduce unknowns. Buffer sprint allocated. | Tech Lead |
| Scope creep: teams request custom features during migration | Medium | Medium | Strict scope (Section 3). Feature requests logged as backlog, not migration blockers. | PM |

## 18Dependencies

| Dependency | Type | Status | Impact if Blocked |
| --- | --- | --- | --- |
| SDK (@brdrwanda/observability) | Software | Available | Cannot migrate any service |
| Grafana Stack (Tempo, Loki, Prometheus, OTel Collector) | Infrastructure | Deployed | Cannot validate traces, logs, metrics |
| Grafana | Infrastructure | Deployed | Cannot create dashboards or alerts |
| Developer capacity | Resource | Shared | Migration delayed. Per-service migration requires 2–7 developer-days. |
| QA capacity | Resource | Shared | Validation phase blocked |
| PM coordination | Resource | Shared | Sprint planning, stakeholder alignment |
| Staging environment | Environment | Available | Cannot test before production |
| CI/CD pipeline | Infrastructure | Available | Cannot deploy migration PRs |
| Kubernetes cluster | Infrastructure | Available | Cannot deploy production. Note: K8s deployments currently lack liveness/readiness probes. |
| Architecture review | Governance | Needed | Observability design decisions may need architect sign-off |

## 19Governance

### RACI Matrix

| Activity | Developer | SRE | Tech Lead | PM | Business |
| --- | --- | --- | --- | --- | --- |
| Service Assessment | R | C | A | I | — |
| Endpoint Inventory | R | C | A | I | — |
| Endpoint Classification | C | C | A | R | C |
| Observability Design | R | R | A | I | — |
| SDK Migration (code) | R | C | A | I | — |
| Dashboard Creation | C | R | A | I | — |
| Alert Configuration | C | R | A | I | — |
| Validation | R | R | A | I | — |
| Production Deployment | C | R | A | I | — |
| Sprint Planning | C | C | C | R | I |
| Stakeholder Updates | I | I | C | R | A |

R = Responsible   A = Accountable   C = Consulted   I = Informed

### Meeting Cadence

| Meeting | Frequency | Attendees | Purpose |
| --- | --- | --- | --- |
| Migration Standup | Daily (15 min) | Developer, SRE | Blockers, progress, next steps |
| Sprint Planning | Bi-weekly | Developer, SRE, Tech Lead, PM | Select services for next sprint, review estimates |
| Sprint Review | Bi-weekly | All + Business stakeholders | Demo migrated services, dashboards, lessons learned |
| Stakeholder Update | Monthly | PM, Tech Lead, Business | Project tracker review, risk update, timeline |

### Decision Process

- Technical decisions (SDK config, metric names, alert thresholds): Developer + SRE decide, Tech Lead approves

- Scope decisions (add/remove services, change timeline): PM proposes, Tech Lead + Business approve

- Escalation path: Developer → Tech Lead → PM → Engineering Manager

### Change Management

- Changes to SDK API: versioned, documented in CHANGELOG, announced in team channel

- Changes to migration approach: discussed in Sprint Planning, documented in this plan

- Changes to timeline: PM updates stakeholders within 24 hours

## 20Definition of Done

A service migration is complete when ALL items are checked. This checklist is signed off by the Tech Lead before marking a service as "Production" in the Project Tracker.

- Endpoint inventory approved — every REST endpoint, Kafka consumer/producer, and scheduled job documented

- Critical endpoints classified — scoring model applied, classification reviewed by PM

- Observability designed — logs, metrics, traces, dashboards, alerts defined for all Critical/High endpoints

- SDK configured — ObservabilityModule.forRoot() with correct serviceName, exporter, instrumentations

- Logs standardized — all logging through SDK's Pino logger; trace_id present on every log line

- Traces verified — end-to-end distributed traces visible in Grafana Tempo with correct span hierarchy

- Metrics exported — /metrics endpoint returns Prometheus format; Prometheus scraping successfully

- Business metrics implemented — all metrics from observability design registering data

- Dashboard published — Service Overview (RED), Runtime, Logs & Traces dashboards provisioned in Grafana

- Alerts configured — platform alerts + service-specific alerts active; notification channel verified

- Legacy removed — zero references to Winston, Morgan, LoggerService, createLoggingContextWithId, custom HttpExceptionFilter

- Legacy packages uninstalled — winston, nest-winston, winston-daily-rotate-file, morgan removed from package.json

- Tests pass — all existing tests pass; no test modifications required beyond logger mocking

- Production deployed — service running in production with SDK

- Hypercare passed — 5 business days stable, no rollback, alerts tuned to production traffic

- Documentation updated — service-specific notes added to migration docs if any deviations from standard playbook

## 21Success Metrics

### Project KPIs

| KPI | Current | Target | How to Measure |
| --- | --- | --- | --- |
| SDK Adoption | 5/11 (45%) | 11/11 (100%) | Count services with SDK in package.json + zero legacy refs |
| Services Fully Migrated | 0/11 (0%) | 11/11 (100%) | Project Tracker — all columns green |
| Endpoint Coverage | Unknown | 100% of endpoints inventoried | Endpoint inventory documents |
| Trace Coverage | ~45% | 100% of HTTP requests carry trace_id | Sample Loki logs; percentage with trace_id present |
| Metric Coverage | 5/11 services | 11/11 services | Prometheus targets — all services up == 1 |
| Dashboard Coverage | 3 dashboards | 6 per service + 2 platform = 68 | Count Grafana dashboards |
| Alert Coverage | 6 platform alerts | 6 platform + service-specific per design | Count active alert rules in Prometheus + Grafana |
| MTTR | Unknown (unmeasured) | < 30 min for P1 | Incident post-mortems — time from alert to root cause |
| MTTD | Unknown (manual detection) | < 5 min | Time from error occurring to alert firing |
| Incident Reduction | Baseline TBD | 30% reduction in first 3 months | Incident tracker |

## 22Lessons Learned

Update this section after every service migration. Sprint retrospective findings that affect the migration approach go here.

### What Worked

- (To be filled after Sprint 1)

### What Didn't Work

- (To be filled after Sprint 1)

### Recommendations for Next Service

- (To be filled after Sprint 1)

### Process Improvements

- (To be filled after Sprint 1)

## 23Appendices

### Appendix A — Microservice Assessment Template

| Field | Value |
| --- | --- |
| Service Name |  |
| Purpose |  |
| Port |  |
| Controllers / Services / Modules |  |
| Dependencies (internal) |  |
| External Systems |  |
| Database (type, ORM, table count) |  |
| Kafka Topics (producer/consumer) |  |
| Business Capabilities |  |
| Critical Flows |  |
| Current Observability (SDK status, legacy refs) |  |
| Migration Complexity (Low/Medium/High) |  |
| Estimated Effort |  |
| Owner |  |
| Status |  |

### Appendix B — Endpoint Inventory Template

| Endpoint | Method | Handler | Business Capability | Consumer | Criticality | Current Logs | Current Metrics | Current Traces |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |

### Appendix C — Metrics Catalogue Template

| Metric Name | Type | Labels | Description | Owner | Dashboard | Alert Condition |
| --- | --- | --- | --- | --- | --- | --- |

### Appendix D — Logging Standards

| Standard | Specification |
| --- | --- |
| Format | JSON (Pino) to stdout |
| Required fields | level, time, pid, hostname, name (service), service_name, environment, version, request_id, correlation_id, trace_id, span_id, msg |
| HTTP request fields | method, url, statusCode, duration_ms |
| Error fields | error_type, error_code, stack (error level only) |
| Sensitive data | Auto-redacted: password, token, secret, authorization, cookie |
| Level usage | info: request lifecycle, business events. warn: 4xx, degraded state. error: 5xx, unhandled exceptions. debug: disabled in production. |

### Appendix E — Tracing Standards

| Standard | Specification |
| --- | --- |
| Protocol | W3C TraceContext (traceparent header) |
| Export | OTLP/HTTP to OTel Collector at :4318 |
| Sampling | Configurable per service. Default: 100% in staging, 10–100% in production. |
| Span naming | HTTP: METHOD /path. Kafka: topic send/receive. DB: Sequelize: OPERATION table. Cron: scheduled/cron/jobName. |
| Required attributes | service.name, service.version, deployment.environment |
| Error recording | Span status set to ERROR + exception recorded as span event |

### Appendix F — Dashboard Checklist

- Service Overview (RED) dashboard created

- Node.js Runtime dashboard created

- Dependencies dashboard created

- Logs & Traces dashboard created

- Business Metrics dashboard created (if applicable)

- Availability dashboard created

- All dashboards use consistent naming: {ServiceName} — {Dashboard Type}

- All dashboards have service name variable selector

- All dashboards have time range selector

- Exemplar links configured (metrics → traces)

- Derived fields configured in Loki (logs → traces)

### Appendix G — Migration Checklist

See Section 14 — Migration Playbook for the full checklist.

### Appendix H — Rollback Checklist

- Previous deployment artifact identified and available

- Rollback command documented and tested in staging

- Rollback trigger defined (error rate threshold, service-down, etc.)

- Communication plan: who to notify, which channels

- Post-rollback verification: error rate baseline, health check, log output

- Root cause analysis initiated within 24 hours

### Appendix I — Definition of Done Checklist

See Section 20 — Definition of Done for the full checklist.

Observability SDK Migration Project Plan · Tugane Platform, BRD Rwanda · Last updated: July 2026